## Slide 1
Portfolio Health Review
Professional Services — Monthly Synthesis · July 2026
Both Zycus S2P projects are in red health, with significant schedule delays and a high blocker count, indicating urgent corrective action is required.

## Slide 2
Portfolio at a Glance
Chart: 
| Red
Projects | 0
Portfolio Snapshot
• 2 active project(s) assessed this cycle
• Average schedule variance: -41.5 days vs. baseline
• Average stakeholder sentiment: -0.14 (-1 to +1)
• Recurring blocker themes: workshop, training, integration
• PM-vs-signal perception gap on: Zycus - Titan S2P Implementation
Only one weekly snapshot has been recorded so far for this portfolio, so week-over-week trend movement cannot be computed yet — insights below are based on the current cross-project snapshot. Run the agent on subsequent weeks (see README) to unlock true time-trend analysis.

## Slide 3
Trends Across the Portfolio
• Both projects are red with >10% task delays
• Average schedule variance of -41.5 days signals widespread lag
• Workshop-related blockers dominate the blocker list (4 instances)
• Titan project shows a perception gap and 0.7 milestone completion rate
• Negative sentiment (-0.14) reflects stakeholder concerns

## Slide 4
Emerging Risks
• Unresolved blockers (301 total) could stall critical deliverables
• Schedule lag of 81 days on Titan may push go‑live beyond target
• Perception gap in Titan risks stakeholder disengagement
• Negative sentiment may erode trust and lead to scope creep

## Slide 5
Project-by-Project Snapshot
Project | RAG | Schedule Variance | Summary
Zycus - UniSan S2P Implementation | Red | -2d | The project is in a red health state because more than 10 % of tasks have slipped past their baseline, with a full 100 % of tasks delayed.
Zycus - Titan S2P Implementation | Red | -81d | The project is in a Red status because more than 10 % of tasks have slipped past baseline, with 64 % of tasks behind schedule and the worst task 81 days late in Phase 2 P2P.

## Slide 6
Recommended Actions
• Schedule a cross‑functional workshop to triage and resolve the 301 open blockers
• Allocate additional resources to Titan to accelerate backlog and reduce 81‑day delay
• Implement a weekly milestone review cadence to monitor progress
• Engage Titan stakeholders in a perception alignment session to close the gap
Narrative source: llm · Generated by the Project Health Reporting Agent